ShopLocal — Part 5

Execution Roadmap

Operated by StormGlide (stormglide.io) — July 2026

Parts 1–4 defined what ShopLocal is, how it operates, how it's priced and launched, and how the flagship delivery feature and the remaining gaps get closed. This document turns that into a sequenced, owned, dated plan: what happens first, who does it, what unblocks what, and how we'll know each phase is actually done. Working assumption carried from Part 4: a team of 2 senior full-stack developers + 1 contract designer + founder on ops — adjust Section 1 and the Month-1 dates if the real team differs.

# 1. Team & Roles

| Role | Who | Primary responsibility |
| --- | --- | --- |
| Founder | You | Entity/legal, merchant interviews, associations & GTM, hiring, fundraising if needed, final call on scope cuts |
| Senior full-stack developer ×2 | To hire/assign | Next.js monolith, Postgres multi-tenant schema, Paystack integration, Mission Control |
| Designer (contract) | To hire/assign | Brand system, storefront theme tokens, marketing site, vertical landing pages |
| KYC reviewer (part-time) | Hire in Month 4 | Mission Control KYC queue — one person handles 60–100 verifications/day (Part 3 §6) |

If the team isn't in place yet, hiring/contracting the two developers and designer is the actual first task — it gates every date in Section 3.

# 2. Phase 0 — Legal, Entity & Validation (Weeks 1–4)

Runs before and slightly overlapping the build. Nothing here needs code. This is the punch list from Part 3 §7, sequenced with owners and dependencies.

| Task | Depends on | Exit criteria |
| --- | --- | --- |
| Trademark / name-availability check on "ShopLocal" (registry, .app/.com, socials) | — | Name cleared, or fallback name chosen before any brand asset is built |
| Register StormGlide's Ghana entity | — | Certificate of incorporation in hand |
| Apply for Paystack business account | Entity registered | Paystack account approved, subaccount/split API access confirmed |
| Register with Ghana Data Protection Commission (Act 843) | Entity registered | Registration number obtained; data protection contact named |
| Accountant ruling on VAT treatment of GHS 466 pricing | Entity registered | Final price confirmed as VAT-inclusive or exclusive |
| Draft Terms of Service, Privacy Policy, merchant agreement, refund policy | Name cleared | Reviewed by counsel (or vetted template), ready to publish at launch |
| 20 merchant interviews — fashion, food, general retail | — | Willingness-to-pay validated at GHS 466 promo price; interview notes logged |
| Soft-commit the "Founding 100" list from interview contacts | Interviews underway | Running list of named, contactable merchants who said yes |
| Buy domain(s) for the cleared name | Name cleared | Domain live, DNS accessible for Month 1 Cloudflare setup |

Phase 0 exit criteria: entity + Paystack account active, name locked, ToS/Privacy drafted, 20 interviews done, Founding 100 list started. Development can start in parallel once the name is locked — don't block Month 1 on the accountant or DPC registration.

# 3. Phase 1 — MVP Build (Months 1–4)

Sequenced from Part 4 §5's v1 cut and Part 3's stack. Each month ends with something a merchant could actually use, not just infrastructure.

## Month 1 — Foundation

- Repo + infra: Next.js (TypeScript) monolith scaffold, Docker + Coolify on Hetzner/DigitalOcean VPS

- Postgres with tenant_id-on-every-row multi-tenant pattern; Cloudflare wildcard DNS + wildcard SSL

- Subdomain resolution: businessname.shoplocal.app routes to the correct tenant

- Merchant auth: my.shoplocal.app portal, phone OTP (WhatsApp/SMS via Meta Cloud API + Arkesel/Hubtel fallback), password option, 2FA scaffold

- Store-creation flow: name + phone → OTP → category → store instantly provisioned

Exit criteria: a phone number can create a tenant and log back into an empty portal.

## Month 2 — Storefront + first vertical

- General Retail vertical template — the simplest, ships first (catalogue, categories, pickup/delivery choice, order tracking)

- Merchant portal: add/edit products, photos, stock; basic branding (logo, colours from curated palette)

- Marketing site v1: hero, pricing page, signup entry point wired into the store-creation flow from Month 1

Exit criteria: a merchant can sign up, pick General Retail, add 5 products, and see a live public storefront.

## Month 3 — Commerce + payments + delivery Phase 1

- Fashion & Clothing and Food & Restaurant vertical templates (variants; order-ahead/short-lived cart)

- Paystack integration: subaccounts, transaction splits, MoMo + card checkout, charge.success webhooks

- Guest checkout (no buyer accounts), order management, WhatsApp one-tap order handling (Confirm / Assign rider / Delivered)

- Delivery Phase 1: rider book, one-tap WhatsApp dispatch, landmark + GhanaPost GPS address capture, delivery OTP, buyer tracking link

Exit criteria: a buyer can complete guest checkout with MoMo, and the merchant can dispatch and prove delivery — this is the flagship feature, don't let it slip.

## Month 4 — Verification, billing, Mission Control, hardening

- KYC flow: Ghana Card + selfie capture, MoMo wallet name-match; Mission Control KYC review queue

- Subscription billing: 30-day free trial (no card/MoMo required), MoMo recurring billing, retry ladder (days 32/35/38), 7-day grace period, pause-not-delete

- Mission Control MVP: tenants list, KYC queue, billing states, basic dispute log

- Backups (nightly pg_dump → R2), monitoring (Sentry + Uptime Kuma + status page), analytics (self-hosted Plausible/Umami)

- Dogfood with 5–10 friendly merchants; fix what breaks before public launch

Phase 1 exit criteria — Part 4's own bar: "one merchant in Accra can sell one item to one buyer, get it delivered with proof, and pay GHS 466 the next month."

# 4. Phase 1.5 — Post-Launch Hardening (Months 5–8)

| Workstream | What ships |
| --- | --- |
| Verticals | Laundry/Home Services + Automobile templates |
| Pricing | Tier 2 & Tier 3 unlocked, annual prepay (2 months free) |
| Domains | Custom domains + "buy your domain through us" registrar service |
| Delivery Phase 2 | Swoove aggregator integration ("Request a rider"), second courier provider for redundancy |
| Catalogue | Instagram import (paste handle → pull posts/photos), CSV/Excel bulk import |
| Trust | Full dispute centre with SLA timers and merchant trust scores |
| Growth | Referral programme, colour/hero customisation for Tier 2+, staff roles & permissions |

# 5. Go-to-Market Execution

Runs in parallel with the build, not after it. Content and relationships take months to compound — start them in Month 2, not at launch.

| Activity | Starts | Notes |
| --- | --- | --- |
| Founding 100 recruitment | Phase 0 (interviews) | Convert interview contacts into a named, contactable pipeline; they lock the GHS 466 promo price for life/24 months |
| Vertical short-video content | Month 2 | 30-second "watch me build a store for X" screen-recordings, one per vertical — start before the product is finished so there's an audience at launch |
| Association outreach | Month 3 | Book demo evenings for launch week: restaurant/caterers associations, tailors' unions, Abossey Okai spare-parts dealers |
| Proof pipeline | Month 4 (first paying merchants) | Film every happy merchant — 30–60s phone video, shop, real numbers; feeds ads by month 3 post-launch |
| Meta/Instagram ads | Public launch | GHS 50–150/day to start; target boutique/laundry/etc. pages and followers in Accra; scale what converts |
| Geography | Launch: Accra only | Density before breadth — Kumasi second, once Accra proves the playbook |

# 6. Metrics & Instrumentation

Instrument the full funnel from day one of Month 2 (the marketing site v1), not retrofitted after launch:

- view → phone entered → OTP passed → category → first product → live → shared → first order → paid

- Weekly cohort report in Mission Control tracking each stage

- Click budgets (Part 4 §4) enforced as regression gates — e.g. buyer checkout ≤ 4 taps + 3 fields + MoMo PIN, merchant "add a product" ≤ ~45 seconds. A release that blows a budget is treated as a bug, not a trade-off.

The one number that governs everything else: trial → paid conversion rate.

- Above ~30–40%: safe to scale ad spend

- Below that: fix onboarding and delivery before spending another cedi on ads

# 7. Risk Register & Open Items

| Gap | Must close by | Owner / mitigation |
| --- | --- | --- |
| Name/trademark risk on "ShopLocal" | Phase 0 | Founder — check registry + socials before any brand spend |
| No legal entity yet blocks Paystack account | Phase 0 | Founder — entity registration is the critical path for Month 3 payments work |
| Data Protection Commission registration (Act 843) | Before public launch | Founder — required for any entity processing personal data |
| Empty-store / trial-to-paid drop-off | Month 4 build | Launch ritual (share-to-complete-onboarding), earn-more-trial, day-7 human WhatsApp check-in |
| MoMo billing failures read as churn | Month 4 build | Retry ladder + billing-date-of-choice + pause-not-delete |
| Rider no-shows / COD cash handling | Month 3 build | Phase 1 delivery keeps merchant's own riders as default; delivery OTP + recorded amounts |
| Aggregator dependency (delivery Phase 2) | Month 5–8 | Two providers (Swoove + backup) behind an internal delivery interface from day one |
| Support quality at launch | Before public launch | Define who answers WhatsApp, hours, escalation; help-centre articles in English + Twi |
| Buyer-side trust (scam perception) | Month 4 build | Receipts, order-tracking page, and the dispute link must exist at launch — this is reputational, not optional |

# 8. Financial Checkpoints

- Breakeven target: 50–100 paying merchants (≈ GHS 23,300–46,600 MRR) against an estimated GHS 15,000–25,000/month burn (small team + infra + ads)

- Infra budget ceiling: stay under ~2% of revenue — roughly USD 40–80/month at launch, under USD 200–300/month at 500 paying merchants

- Indicative build cost: GHS 150,000–250,000 in salaries across the 4-month MVP window (adjust to actual hiring reality)

- Revenue check: 100 paying merchants ≈ GHS 46,600/month; 500 ≈ GHS 233,000–250,000/month

# 9. Immediate Next Actions (This Week)

| # | Action | Why it's first |
| --- | --- | --- |
| 1 | Confirm the real team: hire/contract the 2 developers + designer, or decide the founder is building solo | Every Month-1 date in Section 3 assumes this team exists — it's the actual blocker |
| 2 | Start the "ShopLocal" trademark/name-availability check | Cheapest thing to get wrong late — blocks domain purchase and brand work |
| 3 | Begin scheduling the 20 merchant interviews | Validates the GHS 466 pricing pivot before a line of code is spent building for it |
| 4 | Kick off Ghana entity registration | Gates the Paystack business account, which gates all of Month 3's payment work |
| 5 | Draft a one-page Founding 100 pitch to use in the interviews | Turns validation calls into pipeline instead of one-off conversations |

This roadmap assumes the Part 4 team shape (2 devs + 1 designer + founder) and the Part 3 pricing (GHS 466/933/1,866, 30-day trial, 0% transaction fee). If either changes, Sections 1, 3, and 8 need to be re-cut together — they're load-bearing on each other.